## Delivering
National Institute for Health Research (NIHR) Data Requirements on Performance in Delivering Clinical Research
2019-20 (Quarter 2)
For Performance in Delivering Clinical Research the trust shall publish the following information for every commercial contract clinical trial that it hosts which closed to recruitment in the previous 12 months:
This data will need to be published by the trust within 30 days after the end of each quarter.
Quarter 2
01/10/2018-30/09/2019
Research Ethics Committee Reference Number | IRAS Number | Name of Clinical Trial | Target number of patients agreed? | Minimum number of patients agreed to be recruited | Maximum number of patients agreed to be recruited | Target date to recruit patients agreed? | Date agreed to recruit target number of patients | Total number of patients recruited at the agreed target date | Date trial closed to recruitment | Total number of study participants recruited | Reason for closure of trial (Recruitment finished/ Withdrawn by Sponsor/ Withdrawn by Host) | Comments
17/WM/0146 | 220303 | A Placebo-Controlled, Double-Blind, Parallel-Group, 24-Month Study to Evaluate the Efficacy and Safety of E2609 in Subjects with Early Alzheimer’s Disease (MISSION) | Number Agreed | 4 | 4 | Date Agreed | 2019-01-10 | 2 | 2018-12-31 | 3 | Recruitment Finished | 3 patients consented and randomised to study. There are 5 Tiers of screening. 33 participants consented to study, but only 3 made it through all 5 tiers screening. 4 participants failed at the last Tier. Study closed to recruitment 31/12/2018, those who had consented prior to this date were still going through screening process. 1 of these participants met the criteria for all 5 Tiers and was randomised in this quarter. 13th September 2019 Study Treminated by the DMC.