## Initiating
National Institute for Health Research (NIHR) Data Requirements on Performance in Initiating Clinical Research
2017-18 (Quarter 1, Quarter 2, Quarter 3 and Quarter 4)
Providers of NHS services must submit, within 30 days of the end of each quarter, the following information for every clinical trial (regardless of funder or inclusion in NIHR CRN Portfolio) where the Date Site Selected falls within the previous twelve months:
Quarter 1
01/07/2016 - 30/06/2017
Research Ethics Committee Reference Number | IRAS number | Name of Clinical Trial | Date site invited | Date site selected | Date of HRA Approval | Date site confirmed by Sponsor | Date site was confirmed | Non confirmation status | Date site ready to start | Date of recruitment of first patient | Reasons for Delay | Source of Delay NHS Provider/ Sponsor/Neither
16/LO/1377 | 197114 | A multicentre randomised controlled trial to examine whether the addition of a patient and carer skill sharing intervention improves long-term patient wellbeing following hospital treatment for anorexia nervosa. (TRIANGLE) | 2016-11-22 | 2016-11-22 | 2016-10-26 | 2016-11-22 | 2016-11-22 | N/A | 2016-12-01 | Not this quarter | d) Delays caused by Sponsor - delayed confirmation from sponsor of study open to recruitment at site. Sponsor postponed recruitment start date to March/April 2017 and then postponed again until June 2017. Issues with internet/wifi connectivity on ward hindered recruitment. | Both NHS and Sponsor
Quarter 2
01/10/2016 - 30/09/2017
Research Ethics Committee Reference Number | IRAS number | Name of Clinical Trial | Date site invited | Date site selected | Date of HRA Approval | Date site confirmed by Sponsor | Date site was confirmed | Non confirmation status | Date site ready to start | Date of recruitment of first patient | Reasons for Delay | Source of Delay NHS Provider/ Sponsor/Neither
16/LO/1377 | 197114 | A multicentre randomised controlled trial to examine whether the addition of a patient and carer skill sharing intervention improves long-term patient wellbeing following hospital treatment for anorexia nervosa. (TRIANGLE) | 2016-11-22 | 2016-11-22 | 2016-10-26 | 2016-11-22 | 2016-11-22 | N/A | 2016-12-01 | Not this quarter | d) Delays caused by Sponsor - delayed confirmation from sponsor of study open to recruitment at site. Sponsor postponed recruitment start date to March/April 2017 and then postponed again until June 2017. G) Eligible patients seen during the relevant period but did not consent to participate in the trial - Issues with internet/wifi connectivity on ward hindered recruitment as potential participants may struggle to use the wifi on the ward and did not want to use their own data to connect to the website. | Both NHS and Sponsor
16/NW/0389 | 196438 | Effective Home Support in Dementia Care: Project 2.1 Dementia Early Stage Cognitive Aids New Trial | 2017-05-08 | 2017-06-30 | 2016-06-20 | 2017-06-30 | 2017-09-18 | N/A | 2017-09-18 | Not this quarter | 1st participant consented 11/10/17. This will be reported in Q3 | Neither
Quarter 3
01/01/2017-31/12/2017
Research Ethics Committee Reference Number | IRAS number | Name of Clinical Trial | Date site invited | Date site selected | Date of HRA Approval | Date site confirmed by Sponsor | Date site was confirmed | Non confirmation status | Date site ready to start | Date of recruitment of first patient | Reasons for Delay | Source of Delay NHS Provider/ Sponsor/Neither
16/NW/0389 | 196438 | Effective Home Support in Dementia Care: Project 2.1 Dementia Early Stage Cognitive Aids New Trial (DESCANT) | 2017-05-08 | 2017-06-30 | 2016-06-20 | 2017-06-30 | 18/09/2017 The date originally submitted to CTP was an error. This is the correct date | N/A | 2017-09-18 | 11/10/2017. This date was not submitted for Q3 to CTP in error | D - Sponsor Delays - Planned and agreed later start to allow for cognitive aids to be ordered and delivered prior to recruitment commencing. | Neither
16/NW/0877 | 216860 | Multiple-Dose, Dose-Escalation Study to Assess the Safety, Tolerability, Pharmacokinetics and Pharmacodynamics of LY3303560 in Patients with Mild Cognitive Impairment due to Alzheimer’s Disease or Mild to Moderate Alzheimer’s Disease (LMDD) | 2016-08-15 | 2017-09-15 | 2017-04-05 | 2017-09-15 | 2017-10-10 | N/A | 2017-10-10 | Not this quarter | D) Delays caused by Sponsor - Sponsor delayed confirmation of study open to recruitment at site (i.e., green light). Just as Capacity and Capability checks were complete, Sponsor closed Cohort 1 and requested the site to wait to start recruitment until Cohort 2 had opened. Cohort 2 had not yet opened by Q3 2017/18 | Sponsor
17/LO/0380 | 218003 | A Phase III, multicentre, randomized, double-blind, placebo-controlled, parallel-group, efficacy and safety study of Crenezumab in patients with prodromal to mild Alzheimer's Disease (CREAD II) | 2016-11-09 | 2017-05-22 | 2017-05-18 | 2017-10-06 | 2017-09-07 | N/A | 2017-10-06 | Not this quarter | F) No eligible patients seen during the reported period - Strict patient eligibility criteria 1 patient was consented 21/11/2017, however the patient did not pass the screening process in order to be randomised | Neither
17/WM/0146 | 220303 | A Placebo-Controlled, Double-Blind, Parallel-Group, 24-Month Study to Evaluate the Efficacy and Safety of E2609 in Subjects with Early Alzheimer’s Disease (MISSION) | 2016-12-09 | 2017-08-16 | 2017-08-21 | 2017-09-20 | 2017-08-18 | N/A | 2017-09-12 | Not this quarter | A) Relevant permissions delayed and not granted in time. ARSAC approval was delayed. D) Delays caused by sponsor - Delayed confirmation from sponsor of study open to recruitment at site . Another NHS provider is supplying PET scan for the study. Enhanced training for this had to be done by staff at this NHS provider which delayed confirmation of recruitment being allowed to commence. A patient was consented to the study on 22/12/17 but is still going through screening process and not randomised as yet. | Sponsor
Quarter 4
01/04/2017-31/03/2018
Research Ethics Committee Reference Number | IRAS number | Name of Clinical Trial | Date site invited | Date site selected | Date of HRA Approval | Date site confirmed by Sponsor | Date site was confirmed | Non confirmation status | Date site ready to start | Date of recruitment of first patient | Reasons for Delay | Source of Delay NHS Provider/ Sponsor/Neither
16/NW/0389 | 196438 | Effective Home Support in Dementia Care: Project 2.1 Dementia Early Stage Cognitive Aids New Trial (DESCANT) | 2017-05-08 | 2017-06-30 | 2016-06-20 | 2017-06-30 | 18/09/2017 The date originally submitted to CTP was an error. This is the correct date | N/A | 2017-09-18 | 11/10/2017. This date was not submitted for Q3 to CTP in error | First patient recruited 11/10/2017. D - Sponsor Delays - Planned and agreed later start to allow for cognitive aids to be ordered and delivered prior to recruitment commencing. | Neither
16/NW/0877 | 216860 | Multiple-Dose, Dose-Escalation Study to Assess the Safety, Tolerability, Pharmacokinetics and Pharmacodynamics of LY3303560 in Patients with Mild Cognitive Impairment due to Alzheimer’s Disease or Mild to Moderate Alzheimer’s Disease (LMDD) | 2016-08-15 | 2017-09-15 | 2017-04-05 | 2017-09-15 | 2017-10-10 | N/A | 2017-10-10 | Not this quarter | D) Delays caused by Sponsor - Sponsor delayed confirmation of study open to recruitment at site (i.e., green light). Just as Capacity and Capability checks were complete, Sponsor closed Cohort 1 and requested the site to wait to start recruitment until Cohort 2 had opened. Cohort 2 had not yet opened by Q3 2017/18. C) Study closed by Sponsor - early closure of Phase 1 in preparation for Phase 2. Received confirmation of this 26/01/2018 | Sponsor
17/LO/0380 | 218003 | A Phase III, multicentre, randomized, double-blind, placebo-controlled, parallel-group, efficacy and safety study of Crenezumab in patients with prodromal to mild Alzheimer's Disease (CREAD II) | 2016-11-09 | 2017-05-22 | 2017-05-18 | 2017-10-06 | 2017-09-07 | N/A | 2017-10-06 | Not this quarter | H) Contracting Delays - sub contracts were required for services CWP does not provide. F) No eligible patients seen during the reported period - Strict patient eligibility criteria. One patient was consented 21/11/2017, the patient did not pass the screening process. C) Study closed by Sponsor - global early site closure plan notified 01/03/2018 | Both NHS Provider and Sponsor
17/WM/0146 | 220303 | A Placebo-Controlled, Double-Blind, Parallel-Group, 24-Month Study to Evaluate the Efficacy and Safety of E2609 in Subjects with Early Alzheimer’s Disease (MISSION) | 2016-12-09 | 2017-08-16 | 2017-08-21 | 2017-09-20 | 2017-08-18 | N/A | 2017-09-12 | 2018-03-26 | A) Relevant permissions delayed and not granted in time. ARSAC approval was delayed. D) Delays caused by sponsor - Delayed confirmation from sponsor of study open to recruitment at site . Another NHS provider is supplying PET scan for the study. Enhanced training for this had to be done by staff at this NHS provider which delayed confirmation of recruitment being allowed to commence. 1st patient was consented to the study on 22/12/17 and has been randomised on 26/03/2018. | Sponsor
17/LO/0440 | 217506 | A Randomized, Double-Blind, Placebo-Controlled Study to Evaluate the Safety, Tolerability, Pharmacokinetics and Pharmacodynamics of Multiple Ascending Doses of Intrathecally Administered ISIS 814907 in Patients with Mild Alzheimer's Disease | 2016-09-22 | 2017-06-08 | 2017-06-20 | 2017-07-10 | 2017-07-13 | N/A | Not this quarter | Not this quarter | H) Contracting Delays - sub contracts were required for services CWP does not provide. | NHS Provider