## Initiating
National Institute for Health Research (NIHR) Data Requirements on Performance in Initiating Clinical Research
2018-19 (Quarter 1 and Quarter 2)
Providers of NHS services must submit, within 30 days of the end of each quarter, the following information for every clinical trial (regardless of funder or inclusion in NIHR CRN Portfolio) where the Date Site Selected falls within the previous twelve months:
Quarter 1
01/07/2017 - 30/06/2018
Research Ethics Committee Reference Number | IRAS number | Name of Clinical Trial | Date site invited | Date site selected | Date of HRA Approval | Date site confirmed by Sponsor | Date site was confirmed | Non confirmation status | Date site ready to start | Date of recruitment of first patient | Reasons for Delay | Source of Delay NHS Provider/ Sponsor/Neither | Source of Delay NHS Provider/ Sponsor/Neither
16/NW/0877 | 216860 | Multiple-Dose, Dose-Escalation Study to Assess the Safety, Tolerability, Pharmacokinetics and Pharmacodynamics of LY3303560 in Patients with Mild Cognitive Impairment due to Alzheimer’s Disease or Mild to Moderate Alzheimer’s Disease (LMDD) | 2016-08-15 | 2017-09-15 | 2017-04-05 | 2017-09-15 | 2017-10-10 | N/A | 2017-10-10 | Not this quarter | D) Delays caused by Sponsor - Sponsor delayed confirmation of study open to recruitment at site (i.e., green light). Just as Capacity and Capability checks were complete, Sponsor closed Cohort 1 and requested the site to wait to start recruitment until Cohort 2 had opened. Cohort 2 had not yet opened by Q3 2017/18. C) Study closed by Sponsor - early closure of Phase 1 in preparation for Phase 2. Received confirmation of this 26/01/2018 | Sponsor | Sponsor
17/WM/0146 | 220303 | A Placebo-Controlled, Double-Blind, Parallel-Group, 24-Month Study to Evaluate the Efficacy and Safety of E2609 in Subjects with Early Alzheimer’s Disease (MISSION) | 2016-12-09 | 2017-08-16 | 2017-08-21 | 2017-09-20 | 2017-08-18 | N/A | 2017-09-12 | 2018-03-26 | A) Relevant permissions delayed and not granted in time. ARSAC approval was delayed. D) Delays caused by sponsor - Delayed confirmation from sponsor of study open to recruitment at site. Another NHS provider is supplying PET scan for the study. Enhanced training for this had to be done by staff at this NHS provider which delayed confirmation of recruitment being allowed to commence. 1st patient was consented to the study on 22/12/17 and has been randomised on 26/03/2018. | Sponsor | Sponsor
Quarter 2
01/10/2017 - 30/09/2018
CWP did not initiate any Clinical Trials within this time frame.