## Initiating
National Institute for Health Research (NIHR) Data Requirements on Performance in Initiating Clinical Research
2019-20 (Quarter 3)
Providers of NHS services must submit, within 30 days of the end of each quarter, the following information for every clinical trial (regardless of funder or inclusion in NIHR CRN Portfolio) where the Date Site Selected falls within the previous twelve months:
Quarter 3
01/01/2019 - 31/12/2019
Research Ethics Committee Reference Number | IRAS number | Name of Clinical Trial | Date site invited | Date site selected | Date of HRA Approval | Date site confirmed by Sponsor | Date site was confirmed | Non confirmation status | Date site ready to start | Date of recruitment of first patient | Reasons for Delay | Source of Delay NHS Provider/ Sponsor/Neither | Source of Delay NHS Provider/ Sponsor/Neither
18/WA/0209 | 238724 | Problem Adaptation Therapy For Individuals with Mild to Moderate Dementia and Depression. The PATHFINDER Trial | 2019-08-06 | 2019-10-25 | 2018-06-25 | 2019-10-25 | 2019-11-20 |  | 2019-11-20 | 2019-12-04
19/SC/0264 | 264596 | Dementia Person Aligned Care Team (DPACT) Dementia Support Study | 2019-07-15 | 2019-10-31 | 2019-06-26 | 2019-10-31 | 2019-11-05 |  | 2019-11-05 | 2019-12-23
19/NE/0233 | 239794 | Randomised placebo controlled trial of Pramipexole addition to mood stabilisers for treatment resistant bipolar depression (the PAX-BD study) | 2019-05-31 | 2019-11-15 | 2019-09-04 | 2019-11-15 | 2019-11-27 |  | Awaiting Green Light